## Sheet1
Total Module: 12
Module | Pages | Front-End Corrections | Back-End Correction | Table Name
1.Course | Set Courses | Search | Completed | course
| Set Deperatment | Alert error after inserting the data it is show the error message to fill the details. | Completed | department
| Set Levels | Alert error after inserting the data it is show the error message to fill the details | Completed | level
| Block Tree | Have to work on | Pending
| Tree | Remove the menu | Remove
[5 empty] | Note: | change to header & footer
2. Cirriculam | Set Papers | 1. Add the id field in disable mode, because that is like empty. 2. Alert error after inserting the data it is show the error message to fill the details | Completed | set_papers |  | Search is happen in all the fields
| Set Syllabus | Repeatly alert message is coming for each enter. Data are inserting for each enter. After submiting screen is not refreshing | Check | units |  | While working the screen page not found error occuring.
| Export Data | Clear | Completed | Data fetch only |  | Reload the page display Page not found error
After clearing the Pre ops error only can able to proceed testing
3.Faculty | Add Faculty | 1. After adding the faculty some data are remaining. 2. Image missing | Completed | faculty
| Faculty Pool | Clear | Completed | faculty
| Assign Roles (2 screens) | Remove the Assign button | Completed | faculty
|  | Clear | Completed | faculty
4.Student Base | Add Student | Remove Plus fuctionality | Completed | Student
| Student Pool | Without choosing any dropdown batch dd is displaying. Change the text color to white | Check | student
|  | Without choosing any dropdown batch dd is displaying.Export Function missing | Check
| Archive Students | Displaying all the student list | Check
5.Seasons | Create Season | Check the DD design, alert message missing. Image Missing | Completed | season
| Start season | Alert message missing. | Completed | season
| Timeline | Not Started
| Set Classes | Alert error after inserting the data it is show the error message to fill the details | Completed | set_classes
| Set students | 1.Fetching is not happening. 2.Update is not working | Check | set_student_season
| Student Pool | Clear | Completed | set_student_season
| Total Student | Clear | Completed | set_student_season
| All Clear Student | 1.Season DD data repeating. 2.Section DD data is not fetch. 3.Fetch is not working | Check | set_student_season
| Detained Student | Clear | Completed | set_student_season
| Buffered Student | Fetch is not working | Check | set_student_season
6. Exam Base | Create Exam | Clear
| Start Exam | Clear
| Timelime | Not Started
7. Exam Pre ops | Assign Paper | UI error has to be adjusted and assign btn has to replaced because while choosing the type assign button is working | Completed
| Create slot | 1. Fetch is not happening 2.Plus field is repeating. 3. in paper DD paper is not fetching properly | Check
| Schedule Exam | 1. Plus btn repeating . Alert message wrong | Completed
| Set Mark | 1. Plus btn repeating .
8. Grade Setting | Set course | Clear | Completed
| Set Grade | Clear | Completed
| Export Data | Clear | Completed
Completed
9.Seating Configuration | Set Blocks | Clear | Completed
| Set Rooms | Clear | Completed
| Set Seats | Work in algorithm value is not change according to the data given | Check
10.PWT | Dashboard | Clear | Completed
| Set syllabus | Syllabus is not working | Check
| Set Section | After adding the section it not visible we have to go to dashboard and come back | Check
| Set Q.Paper | After adding the question it not visible we have to go to dashboard and come back | Check
Set Pattern